## ProjectEstimates
Task | Times performed | Estimated Avg (hrs) | Total Hours | Notes
EDW Policy Validations | 127 | 4 | 508 | Policies for validation came from Mindtree. They are being used for our test plan as well. Policies validated is itemized on 'ItemizedValidations' tab. Includes triage of issues and confirmation of requirements.
Project Test Planning (total) | 1 | 40 | 40 | Not including weekly review and updates, so may be underestimated.
Defects and Triage (per week) | 18 | 5 | 90 | Roughly an hour spent per day, over 18 weeks
Project Meetings and Planning (per week) | 18 | 1 | 18
Offshore Training/Analysis of Results | 50 | 0.5 | 25 | Calculated using estimated total number of business days since Sasitha was onboarded to project.
Root Cause Analysis - Data Loading issues (total) | 1 | 10 | 10 | Rough estimate
|  | Estimated Total | 691

## ItemizedValidations
Policies | Date | Assigned User story/ Task
AG12996 | 2019-01-14 | US38196
AG12335 | 2019-01-14 | US38196
AG15108 | 2019-01-14 | US38196
AG13163 | 2019-01-14 | US38196
AG15939 | 2019-01-14 | US38196
AG21500 | 2019-01-16 | US38210
AG17766 | 2019-01-16 | US38210
AG21499 | 2019-01-16 | US38212
AG21499 | 2019-01-16 | US38213
AG21484 | 2019-01-16 | US38198
AG20675 | 2019-01-16 | US38210
AG20531 | 2019-01-21 | US38209
AG20670 | 2019-01-21 | US38209
9516137 | 2019-01-21 | US38209
AG21503 | 2019-01-21 | US38208
9515973 | 2019-01-21 | US38242
AG23116 | 2019-01-21 | US38208_1
AG21530 | 2019-01-21 | US38208_2
9515967 | 2019-01-21 | US38206
9515961 | 2019-01-25 | US38207
AG08095 | 2019-01-25 | US38206
AG01938 | 2019-01-25 | US38206
AG11313 | 2019-01-25 | US38206
AG09188 | 2019-01-25 | US38242
AG08095 | 2019-01-25 | US38208_1
AG34057 | 2019-02-01 | US41069
AG34385 | 2019-02-01 | US41069
AG34057 | 2019-02-01 | US41069
AG34921 | 2019-02-04 | US40453
AG36891 | 2019-02-04 | US41069
AG34921 | 2019-02-04 | US41070
AG34976 | 2019-02-04 | US40325
AG38182 | 2019-02-04 | US40325
9518648 | 2019-02-04 | US41071
AG37049 | 2019-02-04 | US38681
AG34954 | 2019-02-04 | US40433
9518648 | 2019-02-04 | US41104
AG47803 | 2019-02-04 | US47803
AH33229 | 2019-02-04 | US42242
AG46889 | 2019-02-13 | US41288
AG47803 | 2019-02-13 | US41912
AG45807 | 2019-02-15 | US40457
AG54417 | 2019-02-15 | US40457
AG54356 | 2019-02-22 | US42242
AG76099 | 2019-03-15 | US42781
AG58109 | 2019-03-15 | US42299
AG78614 (OOS Policy) | 2019-03-18 | US43633
AG75329 | 2019-03-18 | US41918
AG45756 | 2019-02-22 | US40457
AH38616 | 2019-02-22 | US41640
AH36462 | 2019-02-22 | US41641
AH46819 | 2019-02-22 | US41641
AG69260 | 2019-03-08 | US41641
AG80504 | 2019-03-15 | US41641
AG86505 | 2019-03-15 | US41641
AG77517 | 2019-03-18 | US43523
AG78422 | 2019-03-18 | US43523
AH36377 | 2019-03-22 | Composite Rating Cxml
AH44511 | 2019-03-29 | Composite Rating Cxml
AH46819 | 2019-04-01 | Composite Rating Cxml
AH47848 | 2019-04-01 | US44393
AH47875 | 2019-04-03 | US44240
AH48038 | 2019-04-03 | US42314
AH49391 | 2019-04-03 | US44444
AH50136 | 2019-04-03 | US44296
AH50969 | 2019-04-03 | US45513
AH63543 | 2019-04-03 | US44466
AH52709 | 2019-04-03 | US44446
AH65752 | 2019-04-15 | Mass Test policies
AH65742 | 2019-04-15 | Mass Test policies
AH66935 | 2019-04-15 | Mass Test policies
AH67698 | 2019-04-16 | Mass Test policies
AH68720 | 2019-04-17 | Policies for claims
AH68724 | 2019-04-17 | Policies for claims
AH68722 | 2019-04-17 | Policies for claims
AH68777 | 2019-04-17 | Policies for claims
AH68772 | 2019-04-17 | Policies for claims
AH71007 | 2019-04-19 | Alt Mkt Test
AH79534 | 2019-04-25 | Split Limits
AH79547 | 2019-04-25 | Combined
AH66935 | 2019-05-02 | US44180 & US44176
AH69528 | 2019-05-02 | US44180 & US44176
AH69566 | 2019-05-02 | US44180 & US44176
AH69588 | 2019-05-02 | US44180 & US44176
AH69611 | 2019-05-02 | US44180 & US44176
AH69651 | 2019-05-02 | US44180 & US44176
AH70834 | 2019-05-02 | US44180 & US44176
AH84561 | 2019-05-02 | US44180 & US44176
AH84560 | 2019-05-02 | US44180 & US44176
AH71249 | 2019-05-02 | US44180 & US44176
AH71250 | 2019-05-02 | US44180 & US44176
AH71332 | 2019-05-02 | US44180 & US44176
AH71199 | 2019-05-02 | US44180 & US44176
AH70923 | 2019-05-02 | US44180 & US44176
AH78443 | 2019-05-02 | US44180 & US44176
AH86504 | 2019-05-02 | US44180 & US44176
AH86192 | 2019-05-02 | US44180 & US44176
AH86505 | 2019-05-02 | US44180 & US44176
AH86505 | 2019-05-02 | US44180 & US44176
AH70610 | 2019-05-02 | US44180 & US44176
9535618 | 2019-05-02 | US44180 & US44176
AH86192 | 2019-05-02 | US44180 & US44176
AH86504 | 2019-05-02 | US44180 & US44176
AH86499 | 2019-05-02 | US44180 & US44176
AH79804 | 2019-05-02 | US44180 & US44176
AH84560 | 2019-05-02 | US44180 & US44176
AH69566 | 2019-05-02 | US44180 & US44176
AH71199 | 2019-05-02 | US44180 & US44176
AH71250 | 2019-05-02 | US44180 & US44176
AH78562 | 2019-05-02 | US44180 & US44176
AH86499 | 2019-05-02 | US44180 & US44176
AH73328 | 2019-05-02 | US44180 & US44176
AH78405 | 2019-05-02 | US44180 & US44176
AH73305 | 2019-05-02 | US44180 & US44176
AH78622 | 2019-05-02 | US44180 & US44176
AH71332 | 2019-05-02 | US44180 & US44176
AH76431 | 2019-05-02 | US44180 & US44176
AH86502 | 2019-05-02 | US44180 & US44176
AH78562 | 2019-05-02 | US44180 & US44176
AH70612 | 2019-05-02 | US44180 & US44176
AH71365 | 2019-05-02 | US44180 & US44176
AH78591 | 2019-05-02 | US44180 & US44176
AH73249 | 2019-05-02 | US44180 & US44176
AH69434 | 2019-05-02 | US44180 & US44176
AH84561 | 2019-05-02 | US44180 & US44176
AH69531 | 2019-05-02 | US44180 & US44176