## Sheet1
User Story | Policy Number | Submission Number | Observations | Defect Status | Business Unit | Files to upload | Comments
US 38206 | 9515967 | 13202982, 13203202 | when active driver is added effective date is 01/20/19 and when endorsed it is 01/17/19 1. POL_TERM_PARTY_EFF_DT 2. PARTY_HIST_EFF_DT | Closed | SHS
US 38206 | 9515967 | 13202982, 13203202 | when hired car is added policy effective dt - 01/20/19 and when it endorsed pol_risk_rel_eff_dt is /01/17/19 | Closed | SHS
US 38206 | 9515967 | 13202982, 13203202 | POL_RISK_CVRG_HIST_EFF_DT for Action CODE 'A' IT IS 01/20/19 When Action CODE IS 'E' it is 01/17/19 | Closed | SHS
US 38206 | 9515967 | 13202982, 13203202 | When a vehicle is added Risk place ActionCD is 'A' for which effective is 01/20/19 When it is endorsed Riskplace Action CD is 'E' for which effective date is 01/17/19 | Closed | SHS
US 38207 | 9515961 | 13202797, 13202947 | Issue 1 - When ACTIVEDRVR is added the PARTY_HIST_EXP_DT is 01/17/20 but when Deleted Driver PARTY_HIST_EXP_DT is same | Closed | SHS
US 38208_1 | AG21503 | 13193024, 13193031, 13193045, 13193053, 13193060, 13193067, 13193071, 13193078 | PRC_LIMIT_EFF_DT when Action CODE IS 'A' it is 01/17/19 and when Action CODE is 'E' it is 01/16/19 and for subsequent transactions it same 01/16/19 | Closed | SHS
US 38208_2 | AG23116 | 13209666 , 13209756 , 13209783 | No issues Found | Closed | SHS |  | Validated whole policy data effective dates, premium, deductible, coverages and their action codes
US 38209 | AG20531 | 13188507(New Business) , 13188553 (Cancellation) | No issues Found | Closed | SHS |  | APRP is minus and PRP is zero.
US 38209 | AG20670 | 13189148(New Business) , 13189224(Pro Rate Cancellation) | No issues Found | Closed | SHS |  | Action codes are set accordingly to the objects APRP and PRP values are as per the realtionships
US 38209 | 9516137 | 13209068(New Business) , 13209069(Short Rate Cancellation) | No issues Found | Closed | SHS |  | Action codes are set accordingly to the objects APRP and PRP values are as per the realtionships
US 38242 | 9515973 | 13202973 , 13202995 , 13203159 , 13203250 , 13203318 , 13203418 | No issues Found | Closed | SHS |  | When a coverage gets deleted,Rate Class with MDM_CD gets copied forward
US 38206 | 9515967 | 13202982 | When a vehicle is added OPERATION_FROM_DT has to be Changed to the date when it is endorsed ( Period of Operation) | Closed ( Not the Issue) | SHS
US41104 | 9518648 | 13276352, 13276403, 13276427, 13276453 | The NonOwned risk/coverage structure they’re currently sending is all going to change so yes agree that them sending the risk without a coverage on the new business is incorrect but no point creating a defect to fix until after all the CCM refactoring around NonOwned is done. | OPEN | SHS |  | Risk Coverage Realtionship Risk NOSSEMP has no coverages in EDW for all the Transactions
US41104 | 9518648 | 13276352, 13276403, 13276427, 13276453 | (CVRG_CD = BLKAI )The Limit Value( AMT = 15) which is provided is in incorrect. Liability Limit on the policy is 400000 | Closed | SHS |  | US41841 - Limit amount should be set to Liability Limit amount for BLKAI Limit Issue Policy: AG43411, can use this policy to confirm.
US41104 | 9518648 | 13276427, 13276453 | For Vehicle Level Risk Risk_Hist_EFF_DT when it is deleted with Action Code 'D' 02/15/19 which should be 02/01/19 and when it is enodorsed with Action Code ' E' it is 02/15/19 | Closed | SHS |  | It was fixed on following policies if wish to confirm. Stories: Policy: 9519554 on Submission no: 13308863 for US40896 Policy: 9519614 on Submission no: 13310024 for US40892
US40433 | AG34954 | 13276229, 13276346, 13276358 , 13276372 | Limit Amount for TOW Coverage is 2 which in incorrect. Liability Limit on the policy is 200000 | OPEN | SHS
US40325 | AG34976, AG38182 | AG34976: 13276379, 13276386 AG38182: 13297738, 13297784 | In E1: Policy Term party relationship for driver with activity D and soruce key ACTIVEDRVR.Risk party relationship for driver with activity A and soruce key EXCLEDRVR In E2: 1) Policy Term party relationship for driver with activity D and soruce key EXCLEDRVR 2)risk party relationship for driver with activity A and soruce key ACTIVEDRVR These are incorrect when extraced in EDW | Closed | SHS |  | AG39626 - Fixed The Issue with This Policy Number
US41288 | AG46889 | 13344238 , 13344432 , 13344445 | For the deleted driver with action code 'D' the expiration date is not showing the transaction eff date instead it is showing the policy exp date | Closed | SHS |  | AG54272 - Fixed The issue with This Policy Number
US41912 | AG47803 | 13351012, 13351021, 13351028, 13351043 | For the Risks NOSSELEMP and NOSSEMP, doesnot show coverages in EDW | Closed | SHS |  | Once CCM Refaactoring is done then we can look whether they are sending correct objects
US41912 | AG47803 | 13351012, 13351021, 13351028, 13351043 | For TOW coverage Limit Amount is showing 3 which is incorrect | Open | SHS
| AG45807 | all submissions | Pip Coverage has limit value which is incorrect and it should be either 15k/30k | Open | SHS
US40457 | AG54417 | 13395932 | Policy Term Place expiry date should be transaction effective date | Closed | SHS
US42242 | AG54356 | 13395698, 13395745, 13395762 | Pip Coverage has limit value which is incorrect and it should be either 15k/30k | Open | SHS
US42781 | AG76099 | 13518316, 13518329, 13518336 | No issus found | Closed | SHS
US42299 | AG58109 | 13412839, 13412851 | PIP Limit value is $1530 and deductible is $0. When I looked into the requirements document it is showing different. | Open | SHS
US43633 | AG78614 (OOS Policy) | 13526548 | Limit_Amt for TOW Deduct_Amt for UMPD Coverage_Family_Cd for RECOLL is showing None | Closed | SHS |  | Parent Coverage Relationship for REOTIC which has to be OTHTHANCOL has been fixed or not
US41918 | AG75329 | 13512059, 13512427, 13512570, 13512773, 13512778 |  | OPEN | SHS | ` | It’s an OOS which included Non-Premiums (taxes) being reversed and rolled back on
US42242 | AH33229 | 13536536 | Risk_Party_exp_dt for the LPAUDVIS should be 04/17/19 instead it is 03/19/20 Policy Expiration Date is stil used and shoul dhave used the teasaction date when the delete was performed | Closed | SHS |  | Created following story and assigned to MindTree. US44393 - Additional Interest Party Delete Expiration Date Incorrect
Policy Number | Business Unit | Description
AG78422 | SHS | OOS Transaction
AH38616 | SHS | Mid-Term Cancellation Reinstatement
AH36462 | SHS | OOS Transaction
AH46819 | SHS | Testing Forms
US44393 | AH47848 | 13606782, 13606784 | While wrapping up backend testing for US42242 noticed the expiration dates on the Additional Interests being deleted wasn't set correctly. They were still using the policy expiration date and should have used the transaction date when the delete was performed. | Closed | SHS |  | This is the fix for the policy AH33229
US44240 & US44446 | AH47875&AH52709 | 13607136, 13607126, 13607010, 13607153, 13607153, 13607116 | OTHTHANCOL Coverage having Action Code and Date problems at endorsement. The Coverage Activity is coming through with a value of "AEAA" and Dates are missing on the coverage. See example below. The activity and date issues are also cascading down into the Member and Rating object for the same coverage. | Closed | SHS
US42314 | AH48038 | 13607437 | Following story fixes the towing limit amount issue. | Closed | SHS |  | This is the fix for the Towing Limit amount
US44444 | AH49391 | 13610531, 13610532, 13610533, 13610534, 13610536, 13610537, 13610538 | Suspect his is due to Duck Creek no longer generating the stat data on a deleted coverage but when coverages get deleted and make use of the Peril data we'll need the MindTree process to pull the value from the prior CXML history data. | Closed | SHS
US44296 | AH50136 | 13613113, 13613316, 13613312 | OOS TransactionGroup SourceKey Change | Closed | SHS
US45513 | AH50969 | 13615135, 13615068 | CXML is passing PlateNumber with characters to confirm EDW can support Alpha/Numeric in that column now. | Closed | SHS
| AH63543 | 13683560, 13683559, 13683556, 13683563, 13683562, 13683561, 13683552, 13683541, 13683537, 13683533, 13683500 | OOS with Cancel and Reinstatement | OPEN | SHS |  | TRANSACTION GROUP PART NUMBERS 6 AND 7 HAVE A DIFFERENT TRANSACTION_GROUP_EBI_TXT